## Application VMs
Application Name | TCD to Migrate | Live in VPC | Date of Implementation | Number of VMs
Insurance agent system | June | 2018-06-15 | 2018-06-14 | 3
Bonds Reporting System | June | 2018-06-19 | 2018-06-19 | 2
FXML | June | 2018-06-27 | 2018-06-26 | 2
Unisys Archive system | June | 2018-06-21 | 2018-06-21 | 1
CBC Media Report System | July | 2018-07-17 | 2018-07-17 | 1
TW Files Access Control System | July | 2018-07-15 | 2018-07-15 | 2
Seal Image System | July | 2018-07-22 | 2018-07-22 | 1
TWD Cheque Clearing System | July | 2018-07-22 | 2018-07-22 | 4
TWD Outward Remittance System | July | 2018-07-22 | 2018-07-22 | 3 | 42
Rate Board | July | 2018-07-24 | 2018-07-24 | 1
LEAPS | July | 2018-08-07 | 2018-08-07 | 1
CHAR | August | 2018-08-04 | 2018-08-04 | 1
Cardlink System (NMIP) | August | 2018-08-07 | 2018-08-04 | 2
TWSMS | August | 2018-08-10 | 2018-08-10 | 6
ATM Management System | August |  | 2018-08-28 | 2 | w11gatmbom1a w11gatmepo1a | 85G 120G
TW eACH Gateway | Sept |  |  | 3 | x11geachapp1a x11geachgw1a x11geachgw2a | 420G 140G 140G
EJCIC | Setp |  |  | 6 | w11gejcicdb1a x11gejcicapi1a x11gejcicapi2a x11gejcicapp1a x11gejcicapp2a x11gejcicgw1a | 360G 250G 250G 250G 250G 320G
WTS-TW | July | 2018-07-17 | WTS-TW shares the same Sever with CBCMSTW | 1
DBS TW AIX Infrastructure | Sept |  | 2018-09-03 | 2 | w11gintraap1a w11gintradb1a | 60G 140G
IDEAL3 | Sept |  | 2018-09-03 | 2 | W11GI3APP1A W11RI3APP1A | 110G

## Infra VMs
Application Name | TCD to Migrate | Live in VPC | Date of Implementation | Number of VMs | downtime | LV | hostname | size | window | replication
1Bank AD | Sept |  | 2018-09-15 | 2 | 0:00 |  | w11g1bnkdcs0101 w11g1bnkdcs0102 | 272G 272G | Venkata Narendra BABU GUNDAPANENI |  | ID required: 10.197.228.5-w01admin-REG1 Approver group: PSG_DBSGOV_INFMM Implementer group: PSG_DBSINF_INFMM
Altiris | Sept |  | 2018-09-07 | 3 | day time |  | w11gamsap1a w11gamsdb1a w11gamssap1a w11gamstdb1a w11gamstweb1a | 280G 300G 330G |  |  | 10.231.114.4-w11admin-w11gamsap1a-OS-AMST 10.231.114.5-w11admin-w11gamsdb1a-OS-AMST 10.231.114.6-w11admin-w11gamssap1a-OS-AMST
BlueCoat | Aug |  | 2018-09-21 | 2 | 0:00 |  | w11gbcaa01 w11gbcaa02 | 180G 230G |  |  | 10.231.114.187-w11admin-w11gbcaa01-OS-IMSURFTW 10.230.114.187-w11admin-w11gbcaa02-OS-IMSURFTW
CheckPoint | Aug |  | 2018-08-24 | 2 | 19:00 |  | w11gcpsc01 w11gcpsc02 | 280G 180G |  | done done | 10.230.114.18-w11admin-w11gcpsc01-OS-IMNMSTW 10.231.114.18-w11admin-w11gcpsc02-OS-IMNMSTW
Connect Direct(Staging) | Sept |  | 2018-09-09 | 2 | 13:00~15:00 |  | w11gstaging01 w11gstaging2a | 2240G 2060G |  |  | 10.231.114.9-w11admin-w11gstaging2a-OS-Stage 10.230.114.9-w11admin-w11gstaging01-OS-Stage
Bomgar Remote Support | Aug |  | 2018-08-24 | 1 | 9:00 |  | x11gbomgar1a | 132G |  | done | no id to withdraw
CSS ACS system | Aug |  | 2018-08-24 | 1 | 9:00 |  | w11gcssacs1a | 370G |  | done | 10.231.114.168-w11admin-w11gcssacs1a-OS-PROWATCH
CyberAck | Sept |  | 2018-09-15 | 3 | normal greenzone |  | w11gcybacpm01 w11gcybpsm01 w11gcybpsm02 | 150G 115G 140G |  |  | 10.231.114.163-w11admin-w11gcybacpm01-OS-CYBTW 10.231.114.23-w11admin-w11gcybpsm01-OS-CYBTW 10.230.114.23-w11admin-w11gcybpsm02-OS-CYBTW
DBS TW Citrix system | Sept |  | 2018-09-09 | 3 | dr vpc alreay |  | w11gctx2fa02 w11gctx2fa3a w11gctxsa02 w11gctxsa1a w11gctxsg01 w11gctxsg02 | 180G 200G 70G |  |  | 10.231.114.60-w11admin-w11gctx2fa3a-OS-Citrix 10.231.114.48-w11admin-w11gctxsa1a-OS-CITRIX 10.231.114.197-w11admin-w11gctxsg01-OS-Citrix
Security Tools (lumension) | Aug | 2018-08-03 | 2018-08-10 | 1 |  |  | w11glum01 | 170G |  | complete | PDC
Regional Data Loss Prevention(DLP) | Aug | 2018-08-17 | 2018-08-17 | 1 |  |  | w11gdlpap01 | 200G |  | complete | SDC | 10.230.114.159-w11admin-w11gdlpap01-OS-DLP
Security Information Event Management | Aug | 2018-08-17 | 2018-08-17 | 2 |  |  | x11gsiemep03a x11rsiemep03a | 1060G 1060G |  | complete | PDC SDC | 10.231.114.52-root-x11gsiemep03a-OS-SIEM 10.230.114.2-root-x11rsiemep03a-OS-SIEM
Standard Build | Aug | 2018-08-10 | 2018-08-10 | 4 |  |  | x11gstdbpup1a x11gstdbslog1a x11rstdbpup1a x11rstdbslog1a | 500G 260G 500G 200G |  | complete | PDC PDC SDC SDC
Symantec SCSP Server | Aug | 2018-08-17 | 2018-08-17 | 1 |  |  | w11gscsp01 | 580G |  | complete | PDC | 10.231.114.33-w11admin-w11gscsp01-OS-SCSPTW
Symantec SEPM Server | Aug | 2018-08-17 | 2018-08-17 | 1 |  |  | w11gsepm01 | 140G |  | complete | PDC | 10.231.114.24-w11admin-w11gsepm01-OS-SEPM
Mcfee EPO Server | Aug | 2018-08-17 | 2018-08-17 | 1 |  |  | w11gepo1a | 580G |  | complete | PDC | 10.231.114.19-w11admin-w11gepo1a-OS-EPOTW
|  |  | Total | 30
|  |  | Aug | 15
|  |  | Sept | 15
|  |  | Other | 0
Application Name | TCD to Migrate | Live in VPC | Date of Implementation | Number of VMs | downtime | LV | hostname
Online Storage Devcies | TBC |  |  | 2 | Tobey |  | w11gcmcne1a w11rcmcne1a
14.0195

## Dashboard
Applicatoin System | Application Name | #VMs need to migrate to VPC | #VMs complete migration | percent | progress
| Insurance agent system | 3 | 3 | 100% | 100%
| Bonds Reporting System | 2 | 2 | 100% | 100%
| FXML | 2 | 2 | 100% | 100%
| Unisys Archive system | 1 | 1 | 100% | 100%
| CBC Media Report System | 1 | 1 | 100% | 100%
| TW Files Access Control System | 2 | 2 | 100% | 100%
| Seal Image System | 1 | 1 | 100% | 100%
| TWD Cheque Clearing System | 4 | 4 | 100% | 100%
| TWD Outward Remittance System | 3 | 3 | 100% | 100%
| Rate Board | 1 | 1 | 100% | 100%
| LEAPS | 1 | 1 | 100% | 100%
| CHAR | 1 | 1 | 100% | 100%
| Cardlink System (NMIP) | 2 | 2 | 100% | 100%
| TWSMS | 6 | 6 | 100% | 100%
| ATM Management System | 2 | 0 | 0% | 0%
| TW eACH Gateway | 3 | 0 | 0% | 0%
| EJCIC | 6 | 0 | 0% | 0%
| WTS-TW | 1 | 1 | 100% | 100%
| DBS TW AIX Infrastructure | 2 | 0 | 0% | 0%
| IDEAL3 | 2 | 0 | 0% | 0%
| Total | 42 | 31 | 73.81% | 73.81%
Infra System | Application Name | #VMs need to migrate to VPC | #VMs complete migration | percent | progress
| 1Bank AD | 2 | 0 | 0% | 0%
| Altiris | 3 | 0 | 0% | 0%
| BlueCoat | 2 | 0 | 0% | 0%
| CheckPoint | 2 | 0 | 0% | 0%
| Connect Direct(Staging) | 2 | 0 | 0% | 0%
| Bomgar Remote Support | 1 | 0 | 0% | 0%
| CSS ACS system | 1 | 0 | 0% | 0%
| CyberAck | 3 | 0 | 0% | 0%
| DBS TW Citrix system | 3 | 0 | 0% | 0%
| Security Tools (lumension) | 1 | 1 | 100% | 100%
| Regional Data Loss Prevention(DLP) | 1 | 1 | 100% | 100%
| Security Information Event Management | 2 | 2 | 100% | 100%
| Standard Build | 4 | 4 | 100% | 100%
| Symantec SCSP Server | 1 | 1 | 100% | 100%
| Symantec SEPM Server | 1 | 1 | 100% | 100%
| Mcfee EPO Server | 1 | 1 | 100% | 100%
| Total | 30 | 11 | 36.67% | 36.67%

## Sheet1
Application Name | TCD to Migrate | Live in VPC | Date of Implementation | Number of VMs
Insurance agent system | June | 2018-06-15 | 2018-06-14 | 3
Bonds Reporting System | June | 2018-06-19 | 2018-06-19 | 2
FXML | June | 2018-06-27 | 2018-06-26 | 2
Unisys Archive system | June | 2018-06-21 | 2018-06-21 | 1
CBC Media Report System | July | 2018-07-17 | 2018-07-17 | 1
TW Files Access Control System | July | 2018-07-15 | 2018-07-15 | 2
Seal Image System | July | 2018-07-22 | 2018-07-22 | 1
TWD Cheque Clearing System | July | 2018-07-22 | 2018-07-22 | 4
TWD Outward Remittance System | July | 2018-07-22 | 2018-07-22 | 3
Rate Board | July | 2018-07-24 | 2018-07-24 | 1
Loan Evaluation and Application Processing System in TW (LEAPS) | July | 2018-08-07 | 2018-08-07 | 1
CHAR | August | 2018-08-04 | 2018-08-04 | 1
Cardlink System (NMIP) | August | 2018-08-07 | 2018-08-04 | 2
TW SMS Gateway | August | 2018-08-10 | 2018-08-10 | 6
ATM Management System | August |  | 2018-08-28 | 2
TW eACH Gateway | September |  |  | 3
EJCIC | September |  |  | 6
WTS-TW | July | 2018-07-17 | WTS-TW shares the same Sever with CBCMSTW | 1
DBS TW AIX Infrastructure | September |  | 2018-09-03 | 2
IDEAL3 | September |  | 2018-09-03 | 2
Application Name | TCD to Migrate | Live in VPC | Date of Implementation | Number of VMs
1Bank AD | September |  | 2018-09-15 | 2
Altiris Symantec Management Platform | September |  | 2018-09-07 | 3
BlueCoat Reporting system | August |  | 2018-09-21 | 2
CheckPoint Smart Center | August |  | 2018-08-24 | 2
Connect Direct(Staging) | September |  | 2018-09-09 | 2
Bomgar Remote Support | August |  | 2018-08-24 | 1
CSS ACS system | August |  | 2018-08-24 | 1
CyberAck | September |  | 2018-09-15 | 3
DBS TW Citrix system | September |  | 2018-09-09 | 3
Security Tools (lumension) | August | 2018-08-03 | 2018-08-10 | 1
Regional Data Loss Prevention(DLP) | August | 2018-08-17 | 2018-08-17 | 1
Security Information Event Management | August | 2018-08-17 | 2018-08-17 | 2
Standard Build | August | 2018-08-10 | 2018-08-10 | 4
Symantec SCSP Server | August | 2018-08-17 | 2018-08-17 | 1
Symantec SEPM Server | August | 2018-08-17 | 2018-08-17 | 1
Mcfee EPO Server | August | 2018-08-17 | 2018-08-17 | 1